D.F.S

Don’t Forget Sleep

MVP Development Plan

3-Week Sprint Plan & App Specification

GDG Hackathon • Gemini AI → Rescue Mode

Team: 4 Members

Project Manager • UI/UX Designer • Backend Developer • Frontend Developer

Prepared: May 2026 • Revision 3

Revision 3 Changes: (1) Gemini AI moved from plan generation to Rescue Mode + conversational features. Auto Scheduler is now rule-based. (2) Week 3 refocused from app publishing/pilot distribution to hackathon demo preparation, polish, and presentation. No app store submission required.

# Part 1: App Specification

## 1.1 Product Overview

App Name: D.F.S (Don’t Forget Sleep)

Tagline: Sleep-first scheduling for busy students

Platform: Cross-platform mobile app (Flutter)

Context: GDG organizational hackathon entry. Gemini AI is a required integration.

Core Idea: DFS proactively plans your day around a protected sleep floor using fast rule-based scheduling, and uses Gemini AI to deliver personalized recovery advice and daily insights when life disrupts your sleep.

## 1.2 Tech Stack

| Layer | Technology | Rationale |
| --- | --- | --- |
| Frontend | Flutter (Dart) | Single codebase for Android + iOS. GDG ecosystem alignment. |
| Backend | Firebase / Cloud Functions | Serverless, scales to zero. Auth, Firestore, and Functions in one platform. |
| Database | Cloud Firestore | Real-time sync, offline support, flexible schema. |
| AI Engine (Gemini) | Gemini API | Rescue Mode recovery advice, daily personalized insights. Called via Cloud Functions. |
| Scheduler (NEW) | Rule-Based (Dart) | Client-side scheduling logic. Instant plan generation, no API latency, no hallucination risk. |
| Auth | Firebase Auth | Google Sign-In for frictionless onboarding. |
| Analytics | Firebase Analytics | KPI tracking and crash monitoring. |
| Notifications | Local Notifications | Bedtime reminders, caffeine cutoff alerts. No FCM needed for hackathon. |

## 1.3 Gemini AI Strategy

Gemini is deployed where LLMs excel — empathetic, personalized, conversational responses — rather than rigid structured scheduling.

| Feature | What Gemini Does | Why It’s Better Here |
| --- | --- | --- |
| Rescue Mode | Generates personalized 24h recovery plan in natural language based on hours slept, energy, schedule, and history | Conversational output. Variation feels personal. High hackathon demo impact. |
| Daily Insight | Analyzes check-in patterns, surfaces one actionable observation (e.g., “You sleep 40 min less on Physics Lab days”) | Pattern recognition from small data. Feels magical. Low-risk if occasionally off. |
| Sleep Coaching Chat | Conversational interface: “Should I nap?” or “I have an exam tomorrow, what do I do?” | Stretch goal. Showcases Gemini’s conversational strength for judges. |

### Gemini Prompt Architecture

| Component | Details |
| --- | --- |
| System Prompt | You are a sleep health advisor for university students. Practical, empathetic, evidence-based. Never diagnose. Refer to healthcare if symptoms persist >2 weeks. |
| Context Injected | Sleep floor, hours slept, energy level, today’s schedule blocks, past 7 days check-ins, current time |
| Output Format | JSON: { summary, recovery_steps[], nap_advice{}, caffeine_advice{}, encouragement } |
| Safety | Disclaimer on every response. Referral prompt if <4h sleep 3+ consecutive days. Never recommends medication. |

## 1.4 Feature Breakdown by Module

### Module 1: Auto Scheduler (Rule-Based)

| Feature | Description | MVP Scope |
| --- | --- | --- |
| Schedule Input | Manual entry of classes, work, commitments (time + title) | Manual only. No calendar import. |
| Generate Today Plan (Rule-Based) | Dart engine calculates sleep window (bedtime = wake − floor), slots commitments, identifies free blocks, sets caffeine cutoff (bedtime − 8h) | Client-side. Instant. No API call. |
| Time-Block View | Visual timeline: classes, tasks, sleep, naps, free blocks | Read-only display. No drag-and-drop. |
| 10-sec Check-in | Morning prompt: hours slept + energy (1–5) | Triggers Rescue Mode if underslept. |

### Module 2: Minimum Sleep Floor

| Feature | Description | MVP Scope |
| --- | --- | --- |
| Sleep Floor Selector | User chooses 5h / 6h / 7h minimum | Set during onboarding, changeable in settings. |
| Conflict Detection | Rule engine flags impossible sleep floors | Warning with specific conflict details. |
| Bedtime Lock | Scheduler never places tasks inside sleep window | Enforced in rule-based logic. |

### Module 3: Rescue Mode (Gemini-Powered)

| Feature | Description | MVP Scope |
| --- | --- | --- |
| Underslept Recovery 🤖 | Gemini generates personalized 24h recovery: summary, nap timing, caffeine guidance, adjusted bedtime, encouragement | Full Gemini integration. Core demo feature. |
| Overslept Recovery 🤖 | Gemini provides rhythm reset: avoid late naps, sunlight advice, adjusted bedtime | Conversational output. |
| Recovery Checklist | Gemini’s steps rendered as interactive checklist | Tap to check off items. |
| Daily Insight 🤖 | Gemini analyzes 7 days of check-ins, surfaces one actionable pattern on Home | One-liner card. Updated daily. |

### Module 4: Caffeine + Nap Advisor

| Feature | Description | MVP Scope |
| --- | --- | --- |
| Caffeine Cutoff | Rule-based: bedtime − 8h | Simple calculation. No AI. |
| Nap Advisor | Power nap (10–20 min) if gap <2h, full cycle (~90 min) if ≥2h | Rule-based. In plan view + Rescue output. |

## 1.5 Key Screens

| # | Screen | Purpose | Key Elements |
| --- | --- | --- | --- |
| 1 | Onboarding | First-time setup | 3-step wizard: sleep goal → wake window → schedule |
| 2 | Home / Dashboard | Today’s plan + check-in + AI insight | Time-blocks, Generate Plan button, check-in card, Gemini insight |
| 3 | Schedule Manager | Add/edit commitments | Event list, add/edit/delete, day selector |
| 4 | Plan Detail View | Full time-blocked plan | Color-coded blocks, sleep floor compliance |
| 5 | Rescue Mode | Gemini-powered recovery | Under/overslept toggle, AI advice, checklist |
| 6 | Caffeine + Nap | Quick advisor | Cutoff time, nap recommendation |
| 7 | Settings | Preferences + account | Sleep floor slider, notifications, sign out |
| 8 | Sleep History | Past check-ins + compliance | 7-day chart, compliance rate, streak |

## 1.6 Data Models

### Users Collection

| Field | Type | Description |
| --- | --- | --- |
| uid | string | Firebase Auth UID |
| displayName | string | User’s name |
| sleepFloor | number | Minimum sleep target (5, 6, or 7) |
| preferredWake | string | Wake time (HH:mm) |
| preferredBedtime | string | Bedtime (HH:mm) |
| onboardingComplete | boolean | Onboarding finished |

### Schedule Items (subcollection)

| Field | Type | Description |
| --- | --- | --- |
| title | string | Event name |
| startTime / endTime | string | HH:mm format |
| daysOfWeek | array<number> | 0=Mon, 6=Sun |
| category | string | class ¦ work ¦ personal ¦ other |

### Daily Check-ins (subcollection)

| Field | Type | Description |
| --- | --- | --- |
| date | string | YYYY-MM-DD as doc ID |
| hoursSlept | number | Self-reported hours |
| energyLevel | number | 1–5 scale |
| metSleepFloor | boolean | hoursSlept >= sleepFloor |
| rescueTriggered | boolean | Rescue Mode activated |

### Rescue Sessions (subcollection)

| Field | Type | Description |
| --- | --- | --- |
| date | string | YYYY-MM-DD |
| type | string | underslept ¦ overslept |
| hoursSlept | number | Hours that triggered rescue |
| geminiResponse | object | { summary, recovery_steps[], nap_advice, caffeine_advice, encouragement } |
| checklistCompleted | array<boolean> | Completion per recovery step |

## 1.7 API Endpoints

| Method | Endpoint | Input | Output |
| --- | --- | --- | --- |
| N/A | Client-side scheduler (Dart) | Schedule items, sleep floor, wake time | Time blocks, sleep window, caffeine cutoff, nap window. Instant, no API. |
| POST | /rescuePlan 🤖 | { userId, hoursSlept, energyLevel, todaySchedule[], sleepFloor, last7Days[] } | { summary, recovery_steps[], nap_advice, caffeine_advice, encouragement } |
| POST | /dailyInsight 🤖 | { userId, last7DaysCheckins[], scheduleItems[] } | { insight: string, category: string } |
| POST | /checkin | { userId, date, hoursSlept, energyLevel } | { saved, metSleepFloor, streak } |
| GET | /sleepHistory | { userId, days: 7 } | { checkins[], complianceRate, avgHours } |

# Part 2: 3-Week Sprint Plan

## 2.0 Team Roles

| Role | Person | Responsibilities |
| --- | --- | --- |
| PM | You (Project Manager) | Sprint planning, standups, QA, acceptance testing, demo script, presentation prep |
| UIUX | UI/UX Designer | Wireframes, hi-fi mockups, design system, prototyping, demo flow design, presentation slides |
| BE | Backend Developer | Firebase setup, Cloud Functions, Gemini integration (Rescue Mode + insights), security rules |
| FE | Frontend Developer | Flutter app, rule-based scheduler engine (Dart), all UI screens, state management, notifications |

## 2.1 Week 1: Foundation + Rule-Based Planner

Goal: Set up infrastructure, build the rule-based scheduler, complete core UI designs, and have “Generate Today Plan” working end-to-end by Friday. Planner runs client-side — instant, no API needed.

| Day | PM | UIUX | BE | FE |
| --- | --- | --- | --- | --- |
| Mon | Sprint kickoff, task board setup, define W1 user stories | Research sleep apps, moodboard, begin design system | Firebase project setup (Auth, Firestore). Create collections + rules | Init Flutter project, Firebase SDK config, folder structure + Riverpod |
| Tue | Write acceptance criteria for plan generation. Begin QA plan. | Wireframe: Onboarding (3 screens), Home/Dashboard | Build /checkin Cloud Function. Set up Firestore indexes. | Build Onboarding wizard. Begin rule-based scheduler in Dart. |
| Wed | Review wireframes. Define scheduler rules with FE. | Wireframe: Schedule Manager, Plan Detail View. Deliver. | Begin Gemini integration: /rescuePlan Cloud Function + system prompt. | Complete scheduler: sleep window, conflict detection, caffeine cutoff, nap window. |
| Thu | Test scheduler edge cases (overlaps, impossible floors). Log bugs. | Hi-fi mockups: Onboarding + Home/Dashboard. Export assets. | Test /rescuePlan with sample data. Refine Gemini prompt. | Build Home/Dashboard + time-block view. Wire “Generate Plan”. |
| Fri | E2E QA: onboarding → generate plan. Sprint demo + retro. | Hi-fi: Plan Detail View. Begin Rescue Mode wireframes. | Finalize /rescuePlan output. Fix prompt issues. Save to Firestore. | Build Schedule Manager. Integrate check-in. Polish plan view. |

### Week 1 Dependencies

| Dependency | Impact |
| --- | --- |
| Scheduler is client-side — FE is NOT blocked by BE | FE can build + test scheduler independently all week. |
| FE onboarding needs UIUX wireframes (Tue) | FE uses placeholder UI Mon, swaps in designs Wed. |
| BE works on Gemini in parallel — no FE blocker | BE focuses on prompt engineering + /rescuePlan all week. |

### Week 1 Milestone

“Generate Today Plan” works end-to-end (rule-based, instant).

- User completes onboarding and enters 3+ schedule items

- Tapping “Generate Today Plan” instantly shows a time-blocked plan with protected sleep

- Plan includes caffeine cutoff and nap window

- Check-in submits to Firestore

- BE has working /rescuePlan Gemini endpoint (tested independently)

## 2.2 Week 2: Rescue Mode (Gemini) + Polish

Goal: Integrate Gemini Rescue Mode into the app, build daily insights, polish UI with hi-fi designs. By Friday, both the happy path (good sleep → plan) and the AI recovery path (bad sleep → Gemini advice) should work.

| Day | PM | UIUX | BE | FE |
| --- | --- | --- | --- | --- |
| Mon | Sprint 2 planning. Prioritize Rescue Mode. Review W1 bugs. | Hi-fi: Rescue Mode (underslept + overslept flows, checklist). | Refine /rescuePlan: add 7-day history context. Improve quality. | Conflict warning UI. Apply hi-fi to Onboarding + Dashboard. |
| Tue | Test /rescuePlan with various scenarios. Document output quality. | Hi-fi: Caffeine + Nap card, Sleep History. Component library. | Build /dailyInsight endpoint. Test insight quality. | Build Rescue Mode screen: toggle, loading state for Gemini. |
| Wed | Review Rescue Mode designs + Gemini outputs. Full flow test. | Micro-interactions: check-in, Gemini loading, checklist animations. | Error handling + fallback for Gemini failures. Response caching. | Integrate /rescuePlan API. Build interactive recovery checklist. |
| Thu | Full QA: onboarding → plan → check-in → rescue. File bugs. | Design: empty states, error states, toast messages. | Rate limiting on Gemini calls. Fallback default advice. | Caffeine + Nap card. Daily insight card on Home. Bedtime notification. |
| Fri | E2E QA. Sprint 2 demo + retro. Plan Week 3 demo prep. | Polish all screens. Final asset handoff. | Bug fixes. Gemini prompt hardening. Firestore rules. | Apply hi-fi designs everywhere. Fix integration bugs. |

### Week 2 Milestone

Full happy path + Gemini-powered recovery path working.

- Rescue Mode delivers personalized Gemini recovery advice

- Recovery checklist is interactive

- Daily insight card shows on Home (Gemini-generated)

- Gemini failure shows graceful fallback (rule-based default)

- Caffeine + nap displayed in plan view

- All screens use hi-fi designs

## 2.3 Week 3: Demo Polish + Hackathon Prep

Goal: Harden the app for a live demo, add Sleep History analytics, fix all bugs, prepare the hackathon presentation, and rehearse the demo flow. By Friday, the team is ready to present confidently.

| Day | PM | UIUX | BE | FE |
| --- | --- | --- | --- | --- |
| Mon | Sprint 3 planning. Write demo script: exact screens, flow, talking points. | Design Sleep History screen (chart, compliance). Begin presentation slides. | Build /sleepHistory endpoint. Seed demo data (realistic 7-day check-in history). | Build Sleep History screen (bar chart, compliance %, streak). |
| Tue | Write presentation narrative: problem → solution → demo → impact. Draft talking points. | UX polish: loading states, empty states, error handling. Continue slides. | Safety guardrails: disclaimer, referral prompt after 3+ days <4h. Seed more demo data. | Safety guardrails UI. Pre-load demo account with realistic data. |
| Wed | Full regression QA on demo device. Test exact demo flow 3+ times. Log blockers. | Finalize presentation slides. Create demo screen recordings as backup. | Gemini response caching for demo scenarios. Ensure fast responses for key flows. | Error handling + offline fallback. Ensure smooth transitions between all screens. |
| Thu | Fix critical bugs. First full rehearsal: timed run-through with whole team. | Final visual QA. Fix any design drift. Polish slides. | Pre-cache Gemini responses for demo scenarios. Final security check. | Final bug fixes. Lock demo build. Test on demo device. |
| Fri | Final rehearsal. Prepare backup plan (screen recordings). Team ready. | Support rehearsal. Ensure slides + app visuals are consistent. | Hot-fix standby. Monitor Gemini API status. Backup responses ready. | Final demo build verified. App runs clean on demo device. |

### Week 3: Demo Preparation Checklist

| Task | Owner |
| --- | --- |
| Demo script with exact screen flow and talking points | PM |
| Demo account pre-loaded with realistic schedule + 7-day history | BE + FE |
| Gemini responses pre-cached for demo rescue scenario | BE |
| Backup screen recordings of full demo flow | UIUX |
| Presentation slides (problem → solution → live demo → tech → impact) | PM + UIUX |
| 2+ full timed rehearsals | All |
| Demo device tested, charged, Wi-Fi verified | FE |
| Fallback plan if Gemini API is down (cached responses / rule-based) | BE |

### Week 3 Milestone

Team is demo-ready with rehearsed presentation.

- Sleep History screen shows 7-day chart with compliance rate

- Safety guardrails display disclaimer + referral prompt

- App runs without crashes on demo device

- Demo account has realistic pre-loaded data

- Gemini responses are pre-cached for demo reliability

- Presentation slides finalized

- Team has completed 2+ full rehearsals

- Zero critical bugs

## 2.4 Risks & Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Gemini API down during demo | Low–Medium | Critical — breaks demo | Pre-cache responses for demo scenarios. Rule-based fallback. Screen recording backup. |
| Gemini response quality varies | Medium | Low — variation feels personal | Structured JSON output. Validate before rendering. Hardened system prompt. |
| Gemini API latency during demo | Medium | Medium — awkward pause | Loading animation with empathetic copy. Pre-cache key scenarios. Fill time with narration. |
| 3-week timeline too tight | Medium | Medium | Cut daily insight first if behind. Core = planner + rescue. Daily standups. |
| Designer bottleneck | High | Medium | FE starts with placeholders. Designer front-loads critical screens W1. Design system speeds up. |

## 2.5 Summary: 3-Week Overview

|  | Week 1 | Week 2 | Week 3 |
| --- | --- | --- | --- |
| Theme | Foundation + Rule-Based Planner | Rescue Mode (Gemini) + Polish | Demo Polish + Hackathon Prep |
| PM | Sprint setup, scheduler rules, QA | QA rescue + Gemini, bug triage | Demo script, presentation, rehearsals |
| UIUX | Design system, wireframes, hi-fi core screens | Hi-fi Rescue + Caffeine, micro-interactions | Sleep History, slides, screen recordings |
| BE | Firebase, /checkin, /rescuePlan prompt | /dailyInsight, Gemini hardening, fallbacks | /sleepHistory, demo data, cache responses |
| FE | Flutter scaffold, scheduler, Onboarding, Dashboard | Rescue Mode UI, Caffeine card, insight card | Sleep History, polish, final demo build |
| AI | BE builds /rescuePlan (tested alone) | Gemini live in app. Daily insight. | Responses cached for reliable demo |
| Milestone | Instant plan generation | Gemini Rescue Mode working | Demo-ready + rehearsed |

## 2.6 Post-Hackathon Roadmap

- Google Calendar import (replace manual schedule entry)

- Campus pilot with 20–50 students

- Sleep coaching chat (full conversational Gemini interface)

- Personalization engine (learn from check-in patterns)

- Exam Week Mode (premium feature)

- Campus licensing (B2B2C)